## Sheet1
Number of requirement | Name | Linux Virtual | Check steps |  | Is Acutal Yes/No | Comments | Layer of data gathering | Steps to implement | Baseline document getting steps
1 | Build CRQ information | + | Place VM build CRQ number here |  | + |  | N/A | CRQ000000523649
2 | Firewall CRQ rules to connect to all common services | + | Place CRQ number of the firewall for the same build |  | + |  | N/A | CRQ000000523647
3 | Networking Information – IP, Gateway, VLAN, DNS, NTP | + | Get IP, VLAN, DNS and NTP information from EDS/ Build sheet documentation and place here |  | + | 2 images - one from VM, one from EDS | UI+CMD | 1. Connect to Citrix -(depending on environment -QA or Production) 2. Open terminal application (Putty or Secure CRT) 3. Connect to codeserver. 4. Connect via SSH to target machine. 5. Execute command ifconfig. 6. Save ifconfig output to file. 7. For NTP command will be dig {domain.name}.MX
4 | Create VM in specified VxRail Cluster (see Design Document in sharepoint ) | + | Validate Memory and Processing capacities matching to EDS design specifications |  | + | 2 images - VmWare cluster and EDS | UI | 1. Connect to Vcenter. 2. Search for the target host. 3. Go to VM's 4. Take screenshot of VM configuration and status params | To compare with EDS. 1. GO to Sharepoint project area 2. Navigate to project EDS subfolder 3. Open Server requirements. 4. Take a screenshot of the line with the target machine mentioned
5 | Disk space allocation information from EDS/Build sheet, make visible Compute, Sotrage capacities, also separate disks for root, application and cyber tools, Also CPU information | + | Verify disk spacing allocation is matching to the expected values from specs | Link to the descripion of partitions: https://intranet.prod.edisonintl.com/sites/it/gridcsn/_layouts/15/WopiFrame.aspx?sourcedoc=%7B14453CD8-A571-42A2-90AA-6C15C1BDABD1%7D&file=LINUX-BUILD-CHECKLIST.docx&action=default&CT=1659034418552&OR=DocLibClassicUI | + | 2 images - VmWare cluster and EDS | UI+CMD | 1. Connect to Citrix -(depending on environment -QA or Production) 2. Open terminal application (Putty or Secure CRT) 3. Connect to codeserver. 4. Connect via SSH to target machine. 5. Execute command df -h. 6. Save outcome of command to a file. | To compare with EDS. 1. GO to Sharepoint project area 2. Navigate to project EDS subfolder 3. Open Server requirements. 4. Take a screenshot of the line with the target machine mentioned
6 | Install “base OS” or “minimal” installation packages from Ansible Playbook. Make sure the latest patches are applied [CIP-007 R2] | + | The name of the template used. |  | + | keep as is now | N/A
7 | Set time zone ( Pacific, Los Angeles ) and configure NTP using ntpx.domain.com | + | Log in to CLI, stop chrony (if not used previously, install chrony). Change configuration file (/etc/chrony.conf) to ntpx.domain.com. Save changes, restart chrony, check time sync. Make a screenshot, attach here |  | + |  | UI+CMD | 1. Connect to Citrix -(depending on environment -QA or Production) 2. Open terminal application (Putty or Secure CRT) 3. Connect to codeserver. 4. Connect via SSH to target machine. 5. Execute command timedatectl. 6. Save outcome of command to a file.
8 | Connect from Code Server, validate ssh-key authentifaction | + | Validate Key based authentication by ssh. After successful ssh, make a screenshot showing connection status |  | + |  | UI+CMD | 1. Connect to Citrix -(depending on environment -QA or Production) 2. Open terminal application (Putty or Secure CRT) 3. Connect to codeserver. 4. Connect via SSH to target machine. 5.Take screenshot
9 | Configure the datastores for the VMs | + |  |  | + | Screenshot from VmWare cluster about storage allocation | UI+CMD | 1. Connect to Vcenter. 2. Search for the target host. 3. Go to Hosts 4. Take screenshot of Hosts configuration and status params | To compare with EDS. 1. GO to Sharepoint project area 2. Navigate to project EDS subfolder 3. Open Server requirements. 4. Take a screenshot of the line with the target machine mentioned
10 | Confirm all unnecessary logical ports are disabled [ CIP-007 R1.1 ] | + | by Netstat show open connections and ports |  | + |  | UI+CMD | 1. Connect to Citrix -(depending on environment -QA or Production) 2. Open terminal application (Putty or Secure CRT) 3. Connect to codeserver. 4. Connect via SSH to target machine. 5. Execute command netstat -t. 6. Save outcome of command to a file.
11 | Check Services. Make sure that autofs, sshd,sssd,chronyd, ntpd, syslog are enabled, iptables and selinux disabled | + | On Console, navigate to directory /bin. Run service-control -list command. Make a screenshot, attach here |  | + |  | UI+CMD | 1. Connect to Citrix -(depending on environment -QA or Production) 2. Open terminal application (Putty or Secure CRT) 3. Connect to codeserver. 4. Connect via SSH to target machine. 5. Execute command systemctl list-units --type service. 6. Save outcome of command to a file.
12 | Configure the ID agent to collect the compliance data via Industrial Defender [ CIP-010 R1 ] | - | Screenshot from Industrial Defender, confirming asset is reporting to it | Email confirmation from Compliance team about data gathering | + | We will need to show the daemon/agent running for ID Client | UI+CMD | 1. Connect to Citrix -(depending on environment -QA or Production) 2. Open terminal application (Putty or Secure CRT) 3. Connect to codeserver. 4. Connect via SSH to target machine. 5. Execute command systemctl status 6. Save outcome of command to a file, look for the ID agent. | Potentially to be combined with previous test case
13 | Set the Password Complexity Policy for Local ID’s. [ CIP-007 R5.4 ] [ CIP-007 R5.5, R5,6, R5,7 ] | + | Password complexity policy screenshot |  | + |  | UI+CMD | 1. Connect to Citrix -(depending on environment -QA or Production) 2. Open terminal application (Putty or Secure CRT) 3. Connect to codeserver. 4. Connect via SSH to target machine. 5. Execute command cat /etc/login.defs ¦ grep PASS_ 6. make screenshot.
14 | Configure the server to send logs to Syslog-NG and verify the logging in Splunk [ CIP-007 R4.1 ] | + | check a log information in Splunk, make a screenshot |  | + |  | UI | 1. Navigate to Citrix (depening on envrionment - QA or Production) 2. Open browser, navigate to Splunk for the given environment. 3. Login, in the search bar enter the name of the target machine. 4. Search for events related to target machine. (Example - index=* host=irvoaqawmx01*) 5. Make a screenshot of the events list.
15 | Validate Backup properly configured and schedule is set up for VM | + | Take screenshot from vcenter for backup configuration |  | + |  | UI | 1. Connect to Citrix/Jumbox 2. Open Vcenter. 3. Search for the target host. 4. Scroll to Summary/Custom attributes 5. Take screenshot of the message showing latest backup time
16 | Enroll all accounts (interactive and non-interactive) in the PW [ CIP-007 R5.2, R5.4 ] | + | Enable one by one all account data into cyberark, make a screenshot confirming the action, attach screenshot here |  | + |  | UI | 1. Connect to Citrix/Jumbox 2. Navigate to password Vault/Cyberark. 3. Search for the target host. 4. Make a screenshot with accounts listed.
17 | Set mail.rc for smtp relay ( mail.domain.com ) - If required in project scope | + | on CLI enter the appropriate command to set smtp relay server. Provide screenshot from CLI |  | + |  | UI+CMD | 1. Connect to Citrix -(depending on environment -QA or Production) 2. Open terminal application (Putty or Secure CRT) 3. Connect to codeserver. 4. Connect via SSH to target machine. 5. Execute command nslookup MX 6. Make screenshot.
18 | Register with Patch Management server (Ansible or Satellite ) | + | Connect to network server, enter the VM name into appropriate category for the environment in Linux auto-update file. |  | + |  | UI+CMD | 1. Connect to Citrix -(depending on environment -QA or Production) 2. Open terminal application (Putty or Secure CRT) 3. Connect to codeserver. 4. Connect via SSH to target machine. 5. Execute command subscription-manager status 6. Make screenshot.
19 | Add new host as Authentication Agent in RSA (Install and add 2FA for Windows) [ CIP-005 R2] | + | Check on Logon screen if RSA agent is shown. Attach screenshot. |  | + |  | UI+CMD | 1. Connect to Citrix -(depending on environment -QA or Production) 2. Open terminal application (Putty or Secure CRT) 3. Connect to codeserver. 4. Connect via SSH to target machine. 5. Execute command /opt/pam/bin/64bit/acestatus 6. Make screenshot.
20 | Install AV Agent (McAfee or Sentinel One) via Ansible Playbook (Install application and agent for windows, and AV Suite, if supported, for appliance, if applicable) [ CIP-007 R3.1 ] | + | Make a screenshot from EPO or S1 Console to verify asset is reporting to it |  | + |  | UI | 1. Connect to Citrix/Jumbox 2. Navigate to S1 Console or EPO. 3. Search for the target host. 4. Make a screenshot with accounts listed.
21 | Verify Tanium agent reporting status in console | + | Tanium agents should be up and running and reporting to the console |  | + |  | UI | 1. Connect to Citrix/Jumbox 2. Navigate to Tanium Console. 3. Search for the target host. 4. Make a screenshot with accounts listed.
22 | Check event logs to validate there’s no Critical error | + |  |  | + |  | CMD | 1. Connect to Citrix -(depending on environment -QA or Production) 2. Open terminal application (Putty or Secure CRT) 3. Connect to codeserver. 4. Connect via SSH to target machine. 5. Execute command journalctl 6. Save output to a file, validate no Critical errors in it.
23 | Submit the asset change forms and close Build tasks on CRQ | + | Close all tasks assigned to Build team, make screenshot, attach it here |  | + | Manual, CRQ Review | N/A
24 | Is the asset built with Ansible playbook | - | Make a screenshot if applicable |  | + | Manual, CRQ Review | N/A