## Test Cases
Test ID | Test Case Name | Implementation Steps | RobotFramework Validations | Dependencies | RobotFramework Keywords/Libraries | Expected Results/Outputs
1 | Build CRQ information | CRQ000000523649 | NA | NA | NA | NA
2 | Firewall CRQ rules to connect to all common services | CRQ000000523647 | NA | NA | NA | NA
3 | Networking Information – IP, Gateway, VLAN, DNS, NTP | 1. Connect to Citrix -(depending on environment -QA or Production) 2. Open terminal application (Putty or Secure CRT) 3. Connect to codeserver. 4. Connect via SSH to target machine. 5. Execute command ifconfig. 6. Save ifconfig output to file. 7. For NTP command will be dig {domain.name}.MX | 1. Connect to Target - Establish direct connection to the target machine via WinRM for Windows systems or SSH for Linux systems. 2. Collect All Network Info - Execute all network commands (ifconfig, route, DNS, NTP) in one pass and capture the outputs for analysis while saving the ifconfig data to a file. 3. Validate Against EDS - Compare all collected network data (IP, VLAN, DNS resolution, NTP synchronization) against the Engineering Design Specification documentation and report the validation results. | Engineering Design Specification (EDS) repository - Documentation comparison system Forward and reverse lookup validation Time synchronization verification | SSHLibrary, Execute Command, Should Contain, Should Match Regexp, Get Network Info | 1. IP matches EDS: ${expected_ip} 2. VLAN: ${expected_vlan} 3. DNS resolves correctly 4. NTP server reachable 5. ifconfig output captured
4 | Create VM in specified VxRail Cluster (see Design Document in sharepoint ) | 1. Connect to Vcenter. 2. Search for the target host. 3. Go to VM's 4. Take screenshot of VM configuration and status params | 1. Connect to vCenter API - Establish API connection to VMware vCenter and query the target VM details in the specified VxRail cluster using REST API or PowerCLI. 2. Collect VM Information via API - Use vCenter API calls to gather comprehensive VM configuration data including cluster placement, CPU/memory allocation, hardware version, disk configuration, network adapters, and all VM properties, returning detailed JSON/structured data. 3. Validate Against EDS - Compare all API-collected VM specifications (cluster location, CPU count, memory size, reservations, hardware version, and additional properties) against the Engineering Design Specification and build request requirements to ensure complete compliance. | VMware vCenter for VM existence, cluster placement, CPU/memory configuration verification EDS sheet for specification comparison VMware vSphere API for hardware version and compatibility checks | VMwareLibrary, Get VM Info, Should Be Equal, Compare Values, vCenter API | 1. VM found in cluster: ${cluster_name} 2. CPU count: ${expected_cpu} 3. Memory: ${expected_memory} GB 4. Hardware version: ${hw_version} 5. Screenshot captured from vCenter
5 | Disk space allocation information from EDS/Build sheet, make visible Compute, Sotrage capacities, also separate disks for root, application and cyber tools, Also CPU information | 1. Connect to Citrix -(depending on environment -QA or Production) 2. Open terminal application (Putty or Secure CRT) 3. Connect to codeserver. 4. Connect via SSH to target machine. 5. Execute command df -h. 6. Save outcome of command to a file. | 1. Connect to Target - Establish direct connection to the target machine via WinRM for Windows systems or SSH for Linux systems. 2. Collect System Resources - Execute disk space commands (df -h, lsblk, fdisk), gather CPU information, and capture all compute and storage capacity data while saving outputs to files. 3. Validate Against Build Requirements - Compare all collected data (total disk allocation, partition structure, root/application/cyber tools disk sizes, CPU specifications, filesystem types) against the EDS/Build sheet requirements to ensure proper resource allocation and configuration. | Target VM/Server with SSH/WinRM access for disk space and partition validation Build requirements repository for specification comparison OS-level tools (df, fdisk, lsblk) for filesystem validation | SSHLibrary, Execute Command, Parse Disk Output, Should Be Greater Than, df -h, lsblk | 1. Root: ≥ ${root_size} GB 2. /app: ≥ ${app_size} GB 3. /cyber: ≥ ${cyber_size} GB 4. Total matches EDS requirements 5. Filesystem types verified
6 | Install “base OS” or “minimal” installation packages from Ansible Playbook. Make sure the latest patches are applied [CIP-007 R2] |  | 1. Connect to Target - Establish direct connection to the target machine via WinRM for Windows systems or SSH for Linux systems. 2. Collect OS and Package Information - Execute system commands to gather OS version, installed packages, patch history, kernel version, and Ansible build template details while capturing all outputs for analysis. 3. Validate Against Standards - Compare all collected data (OS version, base packages, security patches, Ansible template, kernel version) against approved standards and CIP-007 R2 compliance requirements to ensure proper installation and current patch levels. | Target VM/Server - SSH/WinRM access for OS version and package verification Package repositories - Package validation Ansible Tower/AWX - Template verification | SSHLibrary, uname -a, rpm -qa, yum history, cat /etc/redhat-release | 1. OS: RHEL ${version} 2. Template: ${template_name} 3. Patches current as of ${date} 4. CIP-007 R2 compliant 5. Kernel: ${kernel_version}
7 | Set time zone ( Pacific, Los Angeles ) and configure NTP using ntpx.domain.com | 1. Connect to Citrix -(depending on environment -QA or Production) 2. Open terminal application (Putty or Secure CRT) 3. Connect to codeserver. 4. Connect via SSH to target machine. 5. Execute command timedatectl. 6. Save outcome of command to a file. | 1. Connect to Target - Establish direct connection to the target machine via WinRM for Windows systems or SSH for Linux systems. 2. Collect Time Configuration - Execute time-related commands (timedatectl, chronyc sources, hwclock) to gather timezone settings, chrony service status, NTP server configuration, and synchronization data while saving outputs to files. 3. Validate Time Settings - Compare all collected time configuration data (timezone setting, chrony service status, NTP server configuration, synchronization status, clock drift) against Pacific/Los Angeles requirements and ntpx.domain.com specifications to ensure proper time management. | Target VM/Server - SSH/WinRM access for timezone and chrony service checks NTP servers - Time synchronization validation System clock APIs - Hardware clock synchronization | SSHLibrary, timedatectl, chronyc sources, Should Contain, Service Status, hwclock | 1. Timezone: America/Los_Angeles 2. Chrony: active (running) 3. NTP: ntpx.domain.com configured 4. Time sync status: synchronized 5. Drift: < 1000ms
8 | Connect from Code Server, validate ssh-key authentifaction | 1. Connect to Citrix -(depending on environment -QA or Production) 2. Open terminal application (Putty or Secure CRT) 3. Connect to codeserver. 4. Connect via SSH to target machine. 5.Take screenshot | 1. Connect to Code Server - SSH directly to the code server (Linux jump box) to prepare for SSH key-based authentication testing. 2. Test Passwordless SSH Authentication - From the code server, attempt SSH connection to target machine using key-based authentication without password prompts, verify the connection succeeds, check authorized_keys file permissions (should be 600), and capture connection details. 3. Validate Authentication Security - Confirm passwordless SSH works from code server to target, verify authorized_keys file contains correct public keys with proper permissions (600), validate SSH configuration, and ensure the jump box authentication chain is properly configured. | Code server/Jump server - SSH connectivity testing Target VM/Server - SSH daemon configuration validation | SSHLibrary, Login With Public Key, Should Succeed, Get File, Check Permissions | 1. SSH connection established 2. Key authentication successful 3. No password required 4. Permissions: 600 on keys 5. Connection screenshot captured
9 | Configure the datastores for the VMs | 1. Connect to Vcenter. 2. Search for the target host. 3. Go to Hosts 4. Take screenshot of Hosts configuration and status params | 1. Connect to vCenter - Establish connection to VMware vCenter and locate the target host in the cluster environment. 2. Collect Datastore Information - Gather all datastore configuration data including VM assignments, available capacity, performance tiers, subscription levels, and capture screenshot of host configuration and status parameters. 3. Validate Datastore Configuration - Compare all collected datastore data (VM placement, available capacity, performance tier, subscription ratios) against cluster standards and application requirements to ensure proper storage allocation and performance compliance. | VMware vCenter - Datastore assignment and capacity verification vSphere Storage APIs - Performance tier and capacity validation | VMwareLibrary, Get Datastore Info, Should Be Equal, Check Capacity | 1. VM on correct datastore: ${datastore_name} 2. Available capacity: ≥ ${min_capacity} GB 3. Performance tier: ${required_tier} 4. Subscription: < ${threshold}% 5. Host screenshot captured
10 | Confirm all unnecessary logical ports are disabled [ CIP-007 R1.1 ] | 1. Connect to Citrix -(depending on environment -QA or Production) 2. Open terminal application (Putty or Secure CRT) 3. Connect to codeserver. 4. Connect via SSH to target machine. 5. Execute command netstat -t. 6. Save outcome of command to a file. | 1. Connect to Target - SSH directly to the target machine to collect port information. 2. Collect Netstat Output - Execute netstat command to gather open ports data and save the output to a file. The test passes if the netstat output can be successfully collected, regardless of which ports are open. 3. Mark for Review - Save the collected netstat output and mark test as PASS if data collection succeeded. The reviewer will accept/reject based on their analysis of the ports, not on automated validation of enabled/disabled status. | Target VM/Server - SSH/WinRM access for port and service verification CIP-007 R1.1 compliance standards for logical port security | SSHLibrary, netstat -tuln, ss -tuln, Should Not Contain, Validate Ports, lsof -i | 1. Only approved ports open 2. Unnecessary services: disabled 3. Port list matches baseline 4. CIP-007 R1.1 compliant 5. Security scan passed
11 | Check Services. Make sure that autofs, sshd,sssd,chronyd, ntpd, syslog are enabled, iptables and selinux disabled | 1. Connect to Citrix -(depending on environment -QA or Production) 2. Open terminal application (Putty or Secure CRT) 3. Connect to codeserver. 4. Connect via SSH to target machine. 5. Execute command systemctl list-units --type service. 6. Save outcome of command to a file. | 1. Connect to Target - Establish WinRM connection to Windows target machines to collect service information. 2. List All Running Services - Execute WinRM commands to list all running services and their statuses, saving the complete service list output to a file. 3. Document Service Status - Save the collected service list for review without automated validation of specific service requirements. The reviewer will verify if required services (autofs, sshd, sssd, chronyd, ntpd, syslog) are enabled and unnecessary services (iptables, selinux) are disabled based on the system type. | Target VM/Server - SSH/WinRM access for service status verification SystemD/Service management APIs - Service configuration validation | SSHLibrary, systemctl status, service-control -list, Should Be Active, Should Be Inactive, chkconfig --list | 1. Required services enabled: autofs, sshd, sssd, 2. chronyd, ntpd 3. Disabled services: iptables 4. SELinux: disabled/permissive 5. Auto-start: configured 6. Service list captured
12 | Configure the ID agent to collect the compliance data via Industrial Defender [ CIP-010 R1 ] | 1. Connect to Citrix -(depending on environment -QA or Production) 2. Open terminal application (Putty or Secure CRT) 3. Connect to codeserver. 4. Connect via SSH to target machine. 5. Execute command systemctl status 6. Save outcome of command to a file, look for the ID agent. | 1. Connect to Target - SSH directly to the target machine to verify Industrial Defender agent installation. 2. Verify ID Agent Installation - Check if the Industrial Defender RPM package is installed on the target machine, which collects services and installed software information for compliance monitoring. 3. Validate ID Agent Compliance - Verify the Industrial Defender agent is properly installed and configured to collect compliance data (services, installed software, configuration baselines) as required by CIP-010 R1 for asset management and monitoring. [Coordinate with Avetic Bayon to confirm proper agent configuration and registration] | Target VM/Server with SSH/WinRM access for ID agent status verification Industrial Defender console for communication and reporting validation CIP-010 R1 compliance standards for asset management requirements | SSHLibrary, Process Should Be Running, HTTP Request, Verify In Console, Check Agent Logs | 1. ID agent: installed and running 2. Asset visible in ID console 3. Compliance data reporting 4. Baseline captured 5. CIP-010 R1 compliant
13 | Set the Password Complexity Policy for Local ID’s. [ CIP-007 R5.4 ] [ CIP-007 R5.5, R5,6, R5,7 ] | 1. Connect to Citrix -(depending on environment -QA or Production) 2. Open terminal application (Putty or Secure CRT) 3. Connect to codeserver. 4. Connect via SSH to target machine. 5. Execute command cat /etc/login.defs ¦ grep PASS_ 6. make screenshot. | 1. Connect to Target - SSH directly to the host machine to collect password policy configuration files. 2. Collect Password Policy Configuration - Execute system commands (cat /etc/login.defs, /etc/security/pwquality.conf, /etc/pam.d/system-auth) to gather password complexity settings, account lockout policies, and expiration parameters while capturing screenshots and saving outputs. 3. Validate Password Compliance - Compare all collected policy data (minimum length, character complexity, password history, account lockout, expiration settings) against CIP-007 R5.4, R5.5, R5.6, R5.7 requirements to ensure proper password security implementation. | Target VM/Server - SSH/WinRM access for password policy verification Active Directory/LDAP - Domain password policy validation | SSHLibrary, Get File, /etc/pam.d/system-auth, Should Match Regexp, Validate PAM Config, pwquality.conf | 1. Min length: 8 characters 2. Complexity: 3 of 4 types 3. History: 5 passwords 4. Lockout: 5 attempts 5. CIP-007 R5.4-R5.7 compliant
14 | Configure the server to send logs to Syslog-NG and verify the logging in Splunk [ CIP-007 R4.1 ] | 1. Navigate to Citrix (depening on envrionment - QA or Production) 2. Open browser, navigate to Splunk for the given environment. 3. Login, in the search bar enter the name of the target machine. 4. Search for events related to target machine. (Example - index=* host=irvoaqawmx01*) 5. Make a screenshot of the events list. | 1. Connect to Splunk and Target - Establish connection to Splunk environment through Citrix browser and SSH connection to target machine for syslog-ng configuration access. 2. Collect Logging Configuration - Execute syslog-ng commands to gather forwarding configuration, generate test log messages, and search Splunk for target machine events while capturing screenshots of event lists and log flows. 3. Validate Logging Compliance - Compare all collected logging data (syslog-ng configuration, test message delivery, Splunk event reception, retention policies, critical event capture) against CIP-007 R4.1 requirements to ensure proper log forwarding and 90-day retention compliance. | Syslog-NG service for log forwarding configuration Splunk environment for log reception and retention verification CIP-007 R4.1 compliance standards for logging requirements | SSHLibrary, SplunkLibrary, Search Logs, Logger Test, Verify Log Entry, Check Config | 1. Syslog-ng: configured and running 2. Test log appears in Splunk 3. Host searchable in Splunk 4. 90-day retention confirmed 5. Splunk screenshot captured
15 | Validate Backup properly configured and schedule is set up for VM | 1. Connect to Citrix/Jumbox 2. Open Vcenter. 3. Search for the target host. 4. Scroll to Summary/Custom attributes 5. Take screenshot of the message showing latest backup time | 1. Connect to vCenter API - Establish API connection to VMware vCenter to query VM backup policy configuration and status. 2. Collect Backup Configuration via API - Use vCenter REST API calls to retrieve VM backup policy details, schedule settings, recent job status, retention policies, and latest backup timestamps in text/JSON format rather than screenshots]. 3. Validate Backup Compliance - Compare all API-collected backup data (applied policy, schedule alignment with RPO, retention settings, job completion status, offsite replication) against data criticality requirements and compliance standards to ensure proper backup protection. | VMware vCenter for backup policy and schedule verification Backup management system for job status and retention validation Offsite replication system for disaster recovery compliance | VMwareLibrary, Get Backup Policy, Should Be Configured, Verify Schedule, Check Job Status | 1. Backup policy: ${policy_name} 2. Schedule: Daily at ${time} 3. Retention: ${days} days 4. Last backup: successful 5. vCenter screenshot captured
16 | Enroll all accounts (interactive and non-interactive) in the PW [ CIP-007 R5.2, R5.4 ] | 1. Connect to Citrix/Jumbox 2. Navigate to password Vault/Cyberark. 3. Search for the target host. 4. Make a screenshot with accounts listed. | 1. Connect to Password Vault - Establish connection to CyberArk/Password Vault through Citrix/Jumpbox and search for the target host. 2. Collect Account Information - Gather all enrolled accounts (interactive and non-interactive), synchronization status, rotation policies, API connectivity, and audit logs while capturing screenshot of accounts listed for target host. 3. Validate Account Management - Compare all collected account data (enrollment status, password rotation, vault integration, checkout/checkin workflow, service account controls, audit logging) against CIP-007 R5.2 and R5.4 requirements to ensure proper privileged account security. | CyberArk Privileged Access Security - Account enrollment and rotation verification CyberArk API - Password vault integration testing Target VM/Server - Account checkout/checkin workflow testing Audit logging systems - Activity monitoring verification | CyberArkLibrary, Get Account Status, Verify Enrolled, Test Checkout, Validate Rotation | 1. All accounts enrolled in PW 2. Sync status: active 3. Checkout/checkin functional 4. Password rotation verified 5. CyberArk screenshot captured
17 | Set mail.rc for smtp relay ( mail.domain.com ) - If required in project scope | 1. Connect to Citrix -(depending on environment -QA or Production) 2. Open terminal application (Putty or Secure CRT) 3. Connect to codeserver. 4. Connect via SSH to target machine. 5. Execute command nslookup MX 6. Make screenshot. | 1. Connect to Target - Establish direct connection to the target machine via WinRM or SSH for Linux systems. 2. Collect Mail Configuration - Execute mail commands (nslookup MX, cat /etc/mail.rc, telnet to SMTP port) to gather relay settings, connectivity status, and send test email while capturing screenshots and saving outputs. 3. Validate SMTP Functionality - Compare all collected mail data (relay server configuration, port connectivity, test message delivery, queue status, monitoring alerts) against project scope requirements to ensure proper email subsystem operation. | Target VM/Server - SSH/WinRM access for mail configuration SMTP relay servers - Connectivity and mail delivery testing Email systems - Test message delivery verification System monitoring tools - Alert configuration validation | SSHLibrary, Get File, Send Mail, Should Succeed, Check Mail Queue | 1. SMTP relay: mail.domain.com 2. Port 25 accessible 3. Test email sent successfully 4. Mail queue: empty 5. Alerts configured
18 | Register with Patch Management server (Ansible or Satellite ) | 1. Connect to Citrix -(depending on environment -QA or Production) 2. Open terminal application (Putty or Secure CRT) 3. Connect to codeserver. 4. Connect via SSH to target machine. 5. Execute command subscription-manager status 6. Make screenshot. | 1. Connect to Target - SSH directly to the target machine to check RSA configuration status. 2. Check RSA Configuration - Verify if RSA authentication is configured on the target system by checking for RSA agent installation, configuration files, and authentication settings. 3. Validate RSA Setup - Confirm RSA is properly configured for two-factor authentication, including agent status, server connectivity, and authentication flow readiness. | Ansible Tower/AWX - System registration verification Patch management systems - Schedule and criticality validation Target VM/Server - Update configuration verification | SSHLibrary, subscription-manager, ansible-inventory, Should Be Registered, yum repolist | 1. Registered with: ${patch_server} 2. Auto-update: configured 3. Repository access verified 4. Patch staging successful 5. Subscription screenshot captured
19 | Add new host as Authentication Agent in RSA (Install and add 2FA for Windows) [ CIP-005 R2] | 1. Connect to Citrix -(depending on environment -QA or Production) 2. Open terminal application (Putty or Secure CRT) 3. Connect to codeserver. 4. Connect via SSH to target machine. 5. Execute command /opt/pam/bin/64bit/acestatus 6. Make screenshot. | 1. Connect to Target - SSH directly to the target machine to check antivirus agent installation status. 2. Check Antivirus Agent Installation - Verify if the antivirus agent (McAfee or SentinelOne) is installed on the target system by checking for agent processes, installation directories, and service status. 3. Validate AV Protection - Confirm the antivirus agent is properly installed, running, and providing real-time protection as required by CIP-007 R3.1 for malware prevention. | Target VM/Server - SSH/WinRM access for agent configuration RSA SecurID tokens - Two-factor authentication testing Emergency access systems - Procedure documentation validation | SSHLibrary, RSALibrary, Test 2FA Login, Verify Agent Status, Check Registration | 1. RSA agent: installed and active 2. 2FA prompt appears on login 3. Token validation successful 4. Console registration confirmed 5. Agent status screenshot captured
20 | Install AV Agent (McAfee or Sentinel One) via Ansible Playbook (Install application and agent for windows, and AV Suite, if supported, for appliance, if applicable) [ CIP-007 R3.1 ] | 1. Connect to Citrix/Jumbox 2. Navigate to S1 Console or EPO. 3. Search for the target host. 4. Make a screenshot with accounts listed. | 1. Connect to AV Console - SSH directly to the target machine to check Sentinel or McAfee installation status. 2. Collect AV Agent Information - Execute antivirus commands to gather agent installation status, real-time protection settings, signature update dates, scan schedules, and exclusion configurations while capturing screenshots of console listings and saving outputs. 3. Validate AV Protection - Compare all collected antivirus data (agent installation, real-time protection status, signature currency, console reporting, scheduled scans, exclusion policies) against CIP-007 R3.1 requirements to ensure proper malware protection and compliance. | SentinelOne Console or McAfee EPO for agent management and reporting verification Ansible Tower/AWX for automated agent deployment validation | SSHLibrary, McAfee Agent Check, S1 Status, Should Contain, AV Scan Test, Console API | 1. AV agent: running 2. Signatures: current 3. Last scan: ${scan_date} 4. Reporting to console 5. Real-time protection: active 6. AV console screenshot captured
21 | Verify Tanium agent reporting status in console | 1. Connect to Citrix/Jumbox 2. Navigate to Tanium Console. 3. Search for the target host. 4. Make a screenshot with accounts listed. | 1. Connect to Tanium Console - SSH directly to the target machine to check tanium agent installation status. 2. Collect Agent Information - Execute Tanium commands to gather agent service status, server connectivity, inventory data, module installations, and test query responsiveness while capturing screenshots of console listings and saving outputs. 3. Validate Agent Functionality - Compare all collected agent data (service status, server communication, inventory reporting, query responsiveness, required modules) against environment requirements to ensure proper Tanium agent operation and data collection. | Target VM/Server - SSH/WinRM access for agent status Tanium console - Inventory and compliance data verification | SSHLibrary, TaniumLibrary, Get Agent Status, Query Asset, Check Modules | 1. Tanium agent: active 2. Console status: online 3. Last check-in: < 5 minutes 4. Query responses successful 5. Console screenshot captured
22 | Check event logs to validate there’s no Critical error | 1. Connect to Citrix -(depending on environment -QA or Production) 2. Open terminal application (Putty or Secure CRT) 3. Connect to codeserver. 4. Connect via SSH to target machine. 5. Execute command journalctl 6. Save output to a file, validate no Critical errors in it. | 1. Connect to Target - SSH directly to the target machine to check event logs. 2. Collect System Logs - Execute logging commands (journalctl, dmesg, /var/log analysis) to gather critical errors, boot messages, service startup status, and log rotation configuration while saving all outputs to files for analysis. 3. Validate Log Health - Compare all collected log data (critical error absence, repeating pattern analysis, clean boot sequence, successful service starts, log rotation settings) against system health standards to ensure error-free operation and proper logging management. | Target VM/Server with SSH/WinRM access for system log analysis System logging service (journald/rsyslog) for event log collection Log rotation configuration for disk space management validation | SSHLibrary, journalctl, dmesg, Should Not Contain, Parse Logs, Check Rotation | 1. No critical errors found 2. No failed services 3. Clean boot sequence 4. All services started successfully 5. Log rotation configured
23 | Submit the asset change forms and close Build tasks on CRQ |  | 1. Connect to Change Management Systems - Establish connection to CRQ and asset change management platforms to access the build request and associated tasks. 2. Collect Change Documentation - Gather all asset change form statuses, CRQ task completion data, mandatory field population, build documentation, and test results while preparing handoff materials for operations team. 3. Validate Change Closure - Compare all collected change data (form approvals, task completions, CRQ closure readiness, documentation archival, handoff completeness) against change management requirements to ensure proper project closure and operational transition. | BMC Helix Remedy - CRQ task completion and closure validation Asset change management systems - Form submission verification Operations handoff systems - Documentation completeness validation | BMC Helix RemedyLibrary, Get CRQ Status, Close Tasks, Update Documentation, Archive Results | 1. All tasks: closed 2. CRQ status: completed 3. Documentation: archived 4. Handoff package ready 5. Screenshots captured
24 | Is the asset built with Ansible playbook |  | 1. Connect to Ansible Tower/AWX - Use the Ansible Tower/AWX API to retrieve job information using the specific job ID from the build process. 2. Pull Job Status via API - Query the job status endpoint using the job ID to retrieve execution status, playbook details, success/failure indicators, and any error messages in structured format 3. Validate Build Compliance - Verify the job completed successfully by checking the job status field, reviewing any warnings or skipped tasks, and confirming the playbook executed without failures to ensure proper automated build completion. | Ansible Tower/AWX - Playbook execution and logging Git repositories - Version control and commit tracking Target VM/Server - Configuration state verification | AnsibleLibrary, Get Playbook Status, Verify No Failures, Log Version, Check Variables | 1. Playbook: ${playbook_name} 2. Status: success 3. No configuration drift 4. Version: ${git_commit} 5. All variables validated

## Requirements
Requirements
Core Testing Infrastructure:
RobotFramework test execution environment
Dedicated Git repository access for test case version control
Remot Server Integration - Test result storage and reporting infrastructure
Itential workflow integration for automated test execution
System Access & Connectivity:
SSH/WinRM connectivity to all target VMs/servers for configuration validation
Citrix access for secure environment connectivity
VMware & Infrastructure APIs:
VMware vCenter/vSphere API - VM management, datastore, and validation
VxRail cluster management API - Cluster placement and configuration validation
Change & Configuration Management:
BMC Helix Remedy REST API - Change request management
Ansible Tower/AWX API - Automation and configuration management
Security & Compliance:
CyberArk API - Privileged account management
Tanium API - Endpoint management and compliance
Antivirus management console APIs (McAfee EPO/SentinelOne) - Security validation
Logging & Monitoring:
Splunk API - Log validation and search capabilities
Syslog-NG server connectivity - Log forwarding validation
Additional Requirements:
Engineering Design Specification (EDS) repository access - Configuration baseline validation